## Slide 1: Final Project

## Slide 2: SmartHealth Clinic
Paper Charts

## Slide 3: Work Breakdown Structure

## Slide 4: Gantt Chart

## Slide 5: Risk Assessment Matrix
Category | Description | Probability | Impact | Mitigation Plan
Operations | Staff resistance | Medium | High | Involve staff in planning and provide thorough training
Operations | API Integration failure | Low | Impact | Conduct phased testing with vendors
Finances | Budget overruns | Low | Medium | Allocate a 15% contingency fund for unforeseen costs
Security | Data breach | Medium | High | Implement encryption and access controls
Operations | Migration downtime | High | Low | Schedule migration during off-hours

## Slide 6: Project Tasks, Dependencies, and Durations
Initial Planning – 4 weeks, no dependencies
System Design – 4 weeks, depends on planning
Development – 8 weeks, depends on design
Data Migration – 8 weeks, depends on development
Testing – 8 weeks, depends on development
Training – 8 weeks, depends on testing
Deployment – 4 weeks, depends on testing

## Slide 7: Data Migration Plan
Extraction: Scan in paper files, use optical character recognition tools like Adobe Acrobat or Foxit Pro to convert into text
Cleaning: Remove duplicates, manually review for misspelling and data entry errors
Mapping: Ensure fields names are planned out and aligned with existing paper records
Validation: Compare data sample pre and post-migration to ensure accuracy
Backup procedures: create full backups before migration, store offline backup drives in fireproof safe offsite

## Slide 8: Entity-Relationship Diagram

## Slide 9: Objectives
Full System Deployment for every module
  6 months
  All active charts migrated
  All staff trained and operational

## Slide 10: Lessons Learned
Plan thoroughly
Keep everyone on the same page
Celebrate the wins
GET THE BUY IN!!!

## Slide 11: Power of communication

## Slide 12: Thank you
Joshua Willis
willis56@iu.edu